## SEPT YTD Report for AF&R
Finance YTD CAPEX Project Report - July to September 2023
Category | Programme | 2023/24 Actuals Sept YTD | 2023/24 Budget Sept YTD | Variance YTD | 2023/24 Full Year Adjusted Budget | % of Full Year Budget Spent | Comments | Ward
Assurance, Finance & Risk | Other | 0 | 6115.96 | 6115.96 | 159486.43 | 0% | For the purchase of handheld parking ticket devices. Budget $14k with Actuals of $3k (Full Year Budget $27k) | District
Community Services | Libraries | 75546.19 | 90961.17 | 15414.98 | 439052.55 | 17.21% | District Wide - Libraries stock: YTD Budget $80k with Actuals of $72k (Full year budget $371k) Programmed to spend 23/24 | District
[7 empty] | Frankton Libraries Furniture and Equipment: YTD Budget $2k with Actuals of $0k (Full year budget $13k). Majority to be used for Kingston Library minor renewals 23/24 | Queenstown-Whakatipu
[7 empty] | Wakatipu Libraries Furniture and Equipment: YTD Budget $5k with Actuals of $0k (Full year budget $27k). To be used for staff workroom refurbishment 23/24 | Queenstown-Whakatipu
[7 empty] | Upper Clutha Libraries Furniture & Equipment: YTD Budget $5k with Actuals of $3k (Full year budget $27k). 23/24 improvements yet to be programmed for Hāwea/Wānaka Libraries | Wanaka-Upper Clutha
Community Services | Parks and Reserves | 8928.33 | 205957.95 | 197029.62 | 2632736.07 | 0.3391% | Tracks and Trails Renewals: YTD Budget $2k with Actuals of $5k (Full Year Budget $549k). Whakatipu focus - Gibbston Trail upgrade, Thompson St to Fernhill connection (active travel route B2) and Arrowtown Chinese Village trail realignment. Wānaka focus - Millenium trail Wānaka Lakefront to Glendhu Bay, Upper Clutha River trail resurfacing and Cameron Creen trail. | District
[7 empty] | Tree Planting Programme: YTD Budget $37k with Actuals of $1k (Full Year Budget $216k) Spring planting programme to be completed end of October. Autumn planting programme underway with planting April/May 2024. | District
[7 empty] | Playground Renewals: YTD Budget $39k with Actuals of $0k (Full year budget $189k) Whakatipu focus - Mcbride Park playground feature replacements. Design options being considered with delivery likely by December 23. Wānaka focus - Luggate Playground installation circa $0.3M to require budget reallocation. | District
[7 empty] | Parks Roading Renewals: YTD Budget $0k with Actuals of $1k (Full year budget $694k) Commitments raised for preseal/reseal. Works to be undertaken November 23 - March 24. $50k planned for St Omers Park footpaths, and $50k for Arrowtown reserve sealed footpaths. | District
[7 empty] | Light Pole Replacements & Amenity Lighting: YTD Budget $0k with Actuals of $0k (Full Year Budget $158k) Replacement of St Omer Park and Wānaka Show Ground Lights planned for delivery Q3. | District
Community Services | Venues and Facilities | 98284.25 | 230638.36 | 132354.11 | 864316.33 | 11.37% | QEC Alpine Aqualand Plant & Equipment Renewals: YTD Budget $166k with Actuals of $28k (Full year budget $424k) $150k ringfenced for Wānaka Basketball hoops, balance to spend during May 24 shutdown | Queenstown-Whakatipu
[7 empty] | QEC - Fit Out Renewals: YTD Budget $40k with Actuals of $61k (Full year budget $186k) Being utilised for minor remedial works. | Queenstown-Whakatipu
[7 empty] | Wānaka Pool - Plant & Equipment Renewals: YTD Budget $20k with Actuals of $2k (Full year budget $108k) Works usually completed during June/July shutdown (TBC timing of 23/24 works). | Wanaka-Upper Clutha
Community Services | Buildings | 21852.91 | 0 | -21852.91 | 4457951.56 | 0% | Ballantyne Rd Rec Cen - Wastewater Site prep: YTD Budget $0k with Actuals of $16k (Full year budget $4.1M) On hold pending Council re-prioritisation process associated with capital planning for draft 2024-34 Long Term Plan. | Wanaka-Upper Clutha
[7 empty] | Jack Tewa Park Prefab Relocation: YTD Budget $0k with Actuals of $6k (Full year budget $355k) Consenting and plan change approved (then work paused before final site is confirmed). On hold pending Council re-prioritisation process associated with capital planning for draft 2024-34 Long Term Plan (incorporated into 516 Ladies Mile stage 1 project). | Arrowtown-Kawarau
Community Services | Parks and Reserves | 383676.95 | 1222638.6 | 838961.65 | 9131616.77 | 4.202% | Wānaka Lakefront Development Plan: YTD Budget $120k with Actuals of $128k (Full year budget $2.7M) Stage 2 - Construction complete by May 23 with minor works including tiles, now completed Aug 23. Stage 5 to be transferred to new project in the December 23 Reforecast. | Wanaka-Upper Clutha
[7 empty] | Coronet Forest Revegetation: YTD Budget $450k with Actuals of $95k (Full year budget $2.6M) Planting manager contract awarded. Planting contractor RFP closed August 23. Evaluating September and to award October. | Arrowtown-Kawarau
[7 empty] | Water Sports Facility & Parking - Wānaka: YTD Budget $151k with Actuals of $17k (Full year budget $817k) The Community Board has agreed a scope change in May to change focus to include a new bridge across stoney creek as a priority with remaining budget to include a carpark. Procurement plan completed and looking to go to market in October. | Wanaka-Upper Clutha
[7 empty] | Glenorchy Carpark & Marina Improvements: YTD Budget $138k with Actuals of $19k (Full year budget $723k) Community engagement complete with concept plans approved April 23. Design complete. Construction planned 23/24 pending contractor pricing under review. | Queenstown-Whakatipu
[7 empty] | Toilet Renewals: YTD Budget $62k with Actuals of $35k (Full year budget $631k) Marine Parade & Shotover Country Sportsfield (Tenders closed Sept 23, under review), Northlake (Toilet ordered & tender closed for PM - 20 week lead time) | District
Community Services | Venues and Facilities | 23482.5 | 200000 | 176517.5 | 2288406.3 | 1.026% | QEC New Indoor Court: YTD Budget $0k with Actuals of $0k (Full year budget $1.2M) Masterplan concept design completed 22/23. On hold pending Council re-prioritisation process associated with capital planning for draft 2024-34 Long Term Plan. | Queenstown-Whakatipu
[7 empty] | Frankton Golf Course Reconfiguration: YTD Budget $200k with Actuals of $0k (Full year budget $800k) Tender for pricing closed Feb. Schedule of works currently being prioritised. Timing of Waka Kotahi upgrade of BP roundabout is deferred later than expected (estimated early 2024) so timing of QLDC reconfiguration works not as critical. Likely for Waka Kotahi funding. 22/23 actuals circa $156k to be reimbursed by Waka Kotahi. $500k to be surplus due to 2024-34 Long term Plan baseline approach and not within strategic priorities. Fencing underway Sept/signage/bins etc. | Queenstown-Whakatipu
[7 empty] | QEC - Carpark Reconfiguration: YTD Budget $0k with Actuals of $23k (Full year budget $306k) Masterplan concept design completed 22/23. On hold pending Council re-prioritisation process associated with capital planning for draft 2024-34 Long Term Plan. | Queenstown-Whakatipu
Community Services | Libraries | 8702.42 | 49034.54 | 40332.12 | 269689.92 | 3.227% | Library Systems: YTD Budget $49k with Actuals of $9k (Full year budget $270k) Planned for Libraries Website update $80k, Security gates Arrowtown and Hāwea March/April $40k, Humanforce project starting January / February 24 $21k, RFID wands $18k. | District
Corporate Services | Information Management | 241228.82 | 291651.14 | 50422.32 | 1497519.67 | 16.11% | Enterprise System: YTD Budget $114k with Actuals of $110k (Full year budget $603k) Program includes consultants supporting the TechnologyOne project pipeline and resource (staffing) backfill to support TechnologyOne CiA transition programme | District
[7 empty] | ICT Projects: YTD Budget $52k with Actuals of $15k (Full year budget $286k) Program includes laptop cybersecurity upgrade, Cloud maturity support, backup audit, Digital Strategy Support, Information Management Transformation project support | District
[7 empty] | ICT Network: YTD Budget $43k with Actuals of $12k (Full year budget $236k) Program includes network improvement projects, IoT Platform enhancements, Wi-Fi and switch upgrades. | District
Corporate Services | Other | 14635 | 3494.84 | -11140.16 | 20968.99 | 69.79% | Emergency Management: YTD Budget $3k with Actuals of $15k (Full year budget $21k) Data projector emergency operations equipment purchased | District
Infrastructure | Buildings | 103381.14 | 114689.52 | 11308.38 | 1902639.82 | 5.434% | Gorge Rd Office Civic Building - Renewal: YTD Budget $1k with Actuals of $17k (Full year budget $244k) Toilet refurbishments, renewals of furniture anddesks to be completed 23/24. Circa $180k forecast. | Queenstown-Whakatipu
[7 empty] | Wānaka Eely Point Jetty/Ramp: YTD Budget $4k with Actuals of $7k (Full year budget $422k) Deferred delivery due to not meetign the draft 2024-34 Long Term Plan baseline criteria.. | Wanaka-Upper Clutha
[7 empty] | Pontoon jetty renewals - Whakatipu: YTD Budget $0k with Actuals of $0k (Full year budget $323k) Procurement plan for construction underway with RFP expected to go to market by Jan 24. Consolidated with other minor Ramp/jetty projects districtwide. | Queenstown-Whakatipu
[7 empty] | Wānaka Jetty 147 replacement: YTD Budget $0k with Actuals of $0k (Full year budget $241k) Procurement plan for construction underway with RFP expected to go to market by January 24. Consolidated with other minor Ramp/jetty projects districtwide. | Wanaka-Upper Clutha
[7 empty] | Healthy Homes: YTD Budget $86k with Actuals of $34k (Full year budget $271k) Phase 2: Arrowtown/Wānaka to run August-November 23. | District
Infrastructure | Camp Grounds | 525 | 0 | -525 | 66380.8 | 0.7909% | Campgrounds - Minor Capex: YTD Budget $0 with Actuals of $1k (Full Year Budget $66k) No works identified at present. Possibly required due to new lease agreement. | District
Infrastructure | Libraries | 71994.24 | 61566.89 | -10427.35 | 17065.29 | 421.9% | Libraries Building Renewals: YTD Budget $61k with Actuals of $67k (Full Year Budget $12k) Emergency works required to remove borer and reinstate wall linings and floors at Kingston Library - budget adjustment to be included in the December Reforecast. | Queenstown-Whakatipu
Infrastructure | Transport | 312881.33 | 1130931.39 | 818050.06 | 9092383.33 | 3.441% | Sealed rd resurfacing: YTD Budget $30k with Actuals of $42k (Full Year Budget $2.1M) Downer contract programmed for completion January-April 24. | District
[7 empty] | Sealed road pavement rehabilitation: YTD Budget $382k with Actuals of $37k (Full Year Budget $2.2M) Tenders closed for Cardrona Valley Road rehab works. Review underway with works programmed for December-April 24 (surface sealing season). Design completed for Lower Shotover Rd with tenders ready to go out. | District
[7 empty] | Unsealed road metalling: YTD Budget $236k with Actuals of $2k (Full year budget $1.4M) Budgets aligned with Waka Kotahi funding. Rolling Downer contract to complete works | District
[7 empty] | Butlers Green Retaining Wall: YTD Budget $30k with Actuals of $7k (Full year budget $634k) The budget of $634k allowed for design and construction of an anchor and mesh style repair option to the wall, however all options are now being reviewed in line with the Infrastructure Committee resolution of February 23. Accordingly, a longer lead time to identify and commission a preferred solution is now anticipated. The remaining $50k budget is required to finalise the heritage impact assessment and design options. It is important to note that the established budget will be insufficient for any likely solution so this deferral signals an intention to invest only. The budget will be updated when a preferred option is selected and costed. | Arrowtown-Kawarau
Infrastructure | Venues and Facilities | 9665.51 | 3086.46 | -6579.05 | 120851.85 | 7.998% | Wānaka Arts Centre - Building Renewals: YTD Budget $0k with Actuals of $0k (Full year budget $50k) Internal/External painting planned 23/24 for teh existing Arts Centre. Awaiting award of contract. | Wanaka-Upper Clutha
[7 empty] | Arrowtown Hall - Renewals: YTD Budget $0k with Actuals of $0k (Full year budget $24k) Required for air conditioning refurbishment. | Arrowtown-Kawarau
Infrastructure | Waste Management | 34977.67 | 130374.24 | 95396.57 | 1332460.65 | 2.625% | Existing Waste Site Consenting: YTD Budget $11k with Actuals of $2k (Full year budget $627k) Landfill consent expires 2032. Morrison Low engaged to draft RFP, which is now targeted for Q3 23/24, followed by procurement. Awaiting remediation pricing for Tucker Beach including consenting. Remediation repairs also required for consent at Wānaka closed landfill and Tuckers Beach. | District
[7 empty] | Existing Whakatipu Waste Facilities: YTD Budget $118k with Actuals of $32k (Full year budget $513k) Currently awaiting a proposal from Waste Management on upgrades required. $450k commitments including Materials Recovery Facility (recycling) pit floor, heating, rollers, belts and pipes. MRF preliminary assessment/design for Frankton Transfer station underway. | Queenstown-Whakatipu
[7 empty] | Public Place Waste Bins: YTD Budget $0k with Actuals of $0k (Full year budget $159k) 23/24 focus on installation of bins purchased 22/23 | District
Infrastructure | Storm Water | 150163.1 | 365884.46 | 215721.36 | 1542071.41 | 9.738% | 3 Waters Renewals: YTD Budget $1.4M with Actuals of $1.3M (Full Year Budget $4.4M) Renewals Works programmed to spend full 23/24 budget. | District
[7 empty] | Rockabilly Gully Erosion Protection (stormwater): YTD Budget $103k with Actuals of $0k (Full year budget $616k) Long lead time for technical services currently indicated; rephased to reflect more realistic start date. Procurement for business case inputs and design to be engaged via legal team. | Wanaka-Upper Clutha
Infrastructure | Waste Water | 329293.03 | 450486.69 | 121193.66 | 2651617.17 | 12.42% |  | District
Infrastructure | Water Supply | 877594.5 | 813411.42 | -64183.08 | 1093903.52 | 80.23% |  | District
Infrastructure | Other | 9960.56 | 0 | -9960.56 | 0 | 0% | 3W Reform Stimulus: close out. Costs to be reallocated to other renewals | District
Infrastructure | Buildings | 115910.2 | 262047.5 | 146137.3 | 1771711.21 | 6.542% | Queenstown Performing Arts Centre: YTD Budget $40k with Actuals of $15k (Full year budget $524k) Remaining budget for removal of QPAC to relocate to Country Lane, Frankton. Pending consent prior to removal (Likely early 24). | Queenstown-Whakatipu
[7 empty] | Luggate Hall Replacement: YTD Budget $108k with Actuals of $59k (Full year budget $361k) Awaiting invoice to close out variation on claims that remain under review. Minor close out works to follow. | Wanaka-Upper Clutha
[7 empty] | Stanley St playcentre relocation: YTD Budget $58k with Actuals of $0k (Full year budget $350k) Ministry of Education has recently advised a delay in their programme, this is likely to be due November 23. This is a one off payment of $350,000 towards the new facility. | Queenstown-Whakatipu
[7 empty] | Frankton Library Fitout of leased space: YTD Budget $33k with Actuals of $9k (Full year budget $203k) Design being modified for new leased area. Procurement expected early 2024. | Queenstown-Whakatipu
Infrastructure | Waste Management | 108835.97 | 253062.72 | 144226.75 | 4307778.32 | 2.526% | Product Stewardship: YTD Budget $26k with Actuals of $0k (Full year budget $157k) Required to respond to incoming Government policy, however timing of this is now later than originally anticipated. Budget to be deferred. | District
[7 empty] | Whakatipu New Waste Facilities: YTD Budget $4k with Actuals of $34k (Full year budget $2.8M) Site assessment of Coneburn undertaken and confirmed as not suitable. Project now on hold for S&AP team to develop options. To be deferred in December reforecast. | Queenstown-Whakatipu
[7 empty] | Organic Waste Management: YTD Budget $77k with Actuals of $37k (Full year budget $467k) Forecast to spend $651k which is an additional $184k that will be reimbursed by Ministry for the Environment (milestone dates February/March 24) to support kerbside collections, Grow Wānaka and Zero Waste Glenorchy initiatives. | District
[7 empty] | Zero Waste District Programme: YTD Budget $110k with Actuals of $29k (Full Year Budget $695k) Service agreements in place which will incur milestone payments (Resourceful communities $212k, Wānaka Community Workshop $41k, One Bike Lightfoot Initiative $39k, Kiwi Harvest $38k, Zero Waste Event work $30k, WAO Circular Economy Programme $108k). | District
Infrastructure | Storm Water | 161947.77 | 206744.26 | 44796.49 | 1168841.48 | 13.86% | Catchment Management Plans - Whakatipu & Wānaka: YTD Budget $71k with Actuals of $16k (Full Year Budget $389k) Contract committed to spend full amount across Whakatipu/Wānana. | District
[7 empty] | Investigations - Whakatipu & Wānaka: YTD Budget $64k with Actuals of $64k (Full Year Budget $382k) Contract with E3 Scientific commenced March 23 for $160k across Whakatipu/Wānaka across 21 locations over 2 years. A contract for stormwater level monitoring for $160k also commenced in May to run through 23/24. | District
[7 empty] | Modelling - Whakatipu & Wānaka: YTD Budget $37k with Actuals of $73k (Full Year Budget $201k) $106k PO's raised for modelling to feed into Catchement Management Plans | District
Infrastructure | Waste Water | 129630.13 | 2084361.34 | 1954731.21 | 12445748.14 | 1.042% | Project Pure Aeration Grid Renewal: YTD Budget $1M with Actuals of $5k (Full year budget $6.1M) Proposal received from supplier with the majority of physical works expected 23/24 with partial deferral to reflect potential delivery into 24/25. | Wanaka-Upper Clutha
[7 empty] | Robins Road Conveyance Upgrade: YTD Budget $726k with Actuals of $16k (Full year budget $4.3M) Detailed design underway with deferral of $4.0M proposed through 2024-34 Long Term Plan baseline criteria process to 2024-2026 for construction. | Queenstown-Whakatipu
[7 empty] | Masterplanning Wastewater: YTD Budget $57k with Actuals of $20k (Full year budget $293k) Eastern corridor and Arrowtown wastewater Optimisation study works ongoing. Masterplanning ongoing related to Gordon rd Pump station. | Arrowtown-Kawarau
Infrastructure | Water Supply | 304977.56 | 568654.84 | 263677.28 | 22200771.46 | 1.374% | Cardrona Water Supply Scheme: YTD Budget $25k with Actuals of $27k (Full year budget $15.1M) QLDC is required to make payment to the developer 23/24 upon completion which is forecast February 24. | Wanaka-Upper Clutha
[7 empty] | Two Mile Water Treatment Plant: YTD Budget $43k with Actuals of $20k (Full year budget $1.0M) 23/24 budget being utilised for the UV rapid deployment project in response to the cryptosporidium outbreak. Emergency installations at Fernhill and 2 Mile due to be completed by March 24 following December 2023 interim treatment measures. | Queenstown-Whakatipu
[7 empty] | Hanley's Farm new Reservoir: YTD Budget $10k with Actuals of $0k (Full year budget $1.7M) Developer led design and construction. Developer agreement is drafted and under negotiation. Majority of funds will be a contribution to built assets. Payment would be on completion by developer. LTP Draft proposed deferral to 24/25 $1.6M. | Queenstown-Whakatipu
[7 empty] | Hanley's Farm PS & Rising/Falling mains: YTD Budget $10k with Actuals of $0k (Full year budget $750k) Developer led design and construction. Developer agreement is drafted and under negotiation. Payment would be on completion by developer as a contribution to built assets. LTP Draft proposed deferral to 24/25 $0.7M. | Queenstown-Whakatipu
[7 empty] | Wānaka Water Treatment: YTD Budget $15k with Actuals of $5k (Full year budget $1.6M) 23/24 budget being utilised for the UV rapid deployment project. Emergency installations at Western Intake, Beacon Point, Wānaka Airport, Corebridge and Luggate. Targeting progressive completion towards June 24. | Wanaka-Upper Clutha
Infrastructure | Transport | 3078579.49 | 3037774.34 | -40805.15 | 21348096.53 | 14.42% | Road to Zero Minor Improvements Programme (Low Cost Low Risk): YTD Budget $2.0M with Actuals of $1.9M (Full year budget $9.8M) Construction underway/scheduled for Hawthorne Rd, Glenorchy Corridor, Lower Shotover Rd, Arrowtown RTZ, Riverbank/Ballantyne, Golf Rd, Capell Ave, Wānaka Corridor, Anderson/Aubrey, Rata St, Aubrey Rd and Cardrona Village. Waka Kotahi Subsisidy 51% sub budget. | District
[7 empty] | Wānaka Pool to School Active Travel: YTD Budget $228k with Actuals of $99k (Full year budget $5.2M) Works programmed for Stage 2 Kellys Flat to Hedditch October 23 to March 24 ($ 1.8M) of which $1.5M is Transport Choice Sub funded, Stage 3 Ballantyne to Golf Course Rd November 23 to Apr 24 ($800k) and Stage 4 State Highway crossing January to May 24 ($1.2M) | Wanaka-Upper Clutha
[7 empty] | Active Travel: YTD Budget $184k with Actuals of $421k (Full year budget $756k) Anderson Rd active travel to be completed by December 23. Route B2 Thompson Street works to commence October 23 and due for completion March 24. Waka Kotahi Subsidy 51% sub budget. | Wanaka-Upper Clutha
[7 empty] | Whakatipu Public Transport (Low Cost Low Risk): YTD Budget $37k with Actuals of $60k (Full year budget $662k) Tranche 2 construction contract practical completion reached June 23, with minor close out works to follow 23/24 along with Tranche 3 Design and consultation. Otago Regional Council 51% sub budget. | Queenstown-Whakatipu
[7 empty] | Wānaka Masterplan Update: YTD Budget $0k with Actuals of $51k (Full year budget $618k) Contract for network optimisation single stage business case commenced September 23. Waka Kotahi Subsidy 51% sub budget. | Wanaka-Upper Clutha
[7 empty] | Capell Ave Road Formation: YTD Budget $85k with Actuals of $0k (Full year budget $511k) Formation of this road is subject to a Heads of Agreement between QLDC and local developers. Negotiations regarding the scope and design remain ongoing, delaying implementation. Budget is retained in the current financial year to meet internal costs associated with the ongoing negotiations, business case and early design. $384k proposed to defer to 25/26 through draft LTP24 process and Dec reforecast. Waka Kotahi Subsidy 51% sub budget. | Wanaka-Upper Clutha
Infrastructure | Venues and Facilities | 2205.51 | 0 | -2205.51 | 547171.45 | 0.4031% | Building Management System: YTD Budget $0k with Actuals of $1k (Full year budget $417k) Designs complete. Awaiting delivery of equipment. Implementation expected to commence January 24. | District
[7 empty] | Queenstown Events Centre Energy Upgrade: YTD Budget $0k with Actuals of $1k (Full year budget $130k) LTP24 baseline criteria review proposed deferral of this project to year 3 due to funding constraints. | Queenstown-Whakatipu
Infrastructure | Other | 205532.58 | 377886.25 | 172353.67 | 1483720.92 | 13.85% | Queenstown Priority Growth Corridors: YTD Budget $266k with Actuals of $122k (Full year budget $1.2M) $0.8M proposed to defer to 24/25 per draft 2024-34 Long Term Plan process. Establishment Report complete. Remaining 23/24 budget to support preparation for Ladies Mile SPZ (Special Purposes Zone) hearing. Activities, defined in the establishment report will be progressed in 24/25. | Arrowtown-Kawarau
[7 empty] | Wānaka Airport CAA Requirements: YTD Budget $111k with Actuals of $84k (Full year budget $256k) Draft Capital Plan and Functional Strategy delivered and integrated into draft Long Term Plan preparations. Part 139 compliance deliverables have triggered the need to review Wānaka Airport management structure and the current services agreement in place. Investigative work underway to explore options. | Wanaka-Upper Clutha
PMO - Project Management Office | Waste Management | 10048.8 | 24000 | 13951.2 | 4325235.61 | 0.2323% | Wānaka New Waste Facilities: YTD Budget $24k with actuals of $10k. In process for tender for design (tenders reviewed August 23). Likely to award contract in October and commence concept design by November 23. $350k to remain in 23/24 with balance deferred through the December reforecast. | Wanaka-Upper Clutha
PMO - Project Management Office | Storm Water | 427859.56 | 40500 | -387359.56 | 7879293.27 | 5.43% | Aubrey Rd Rec Reserve Stormwater detention pond: YTD Budget $0k with Actuals of $380k (Full year budget $0k) Detailed design completed and reviewed by ECG & PCG February 23, with the decision proposed to defer commencement of construction of the detention pond on Kelly's Flat to 2027 at present. Physical works for the stormwater pipe on Aubrey road completed August 23. Budget to be increased through the December Reforecast to reimburse the developer for Anderson Road soak pits. | Wanaka-Upper Clutha
[7 empty] | Kingston HIF New Scheme Stormwater: YTD Budget $34k with Actuals of $19k (Full year budget $7.9M) Design and procurement of the stormwater scheme is being managed by the developer (represented by Hadley Consultants). Detailed design is complete and the earthworks consent has been granted. Consultation with the Three Waters National Transition Unit and funding determinations are pending. Next step is procurement/construction. | Queenstown-Whakatipu
PMO - Project Management Office | Waste Water | 6263878.86 | 7792695.07 | 1528816.21 | 48709795.02 | 12.86% | Marine Parade Pumpstation Electrical Upgrade: YTD Budget $46k with Actuals of $28k (Full year budget $125k) A designation is required to consent the pump station in the new location, and is expected to be publicly notified. Detailed design completed May 2023 and remains under review. Construction funding was deferred to 28/29 through Annual Plan 2023-24 due to funding constraints. | Queenstown-Whakatipu
[7 empty] | Project Pure Upgrade Wastewater: YTD Budget $3.5M with Actuals of $2.6M (Full year budget $4.7M) Construction commenced April 22 and is scheduled for completion Dececember 23. | Wanaka-Upper Clutha
[7 empty] | Upper Clutha Conveyance Scheme: YTD Budget $394k with Actuals of $276k (Full year budget $1.8M) Detailed design has commenced and is planned to be completed by the end of 2023. The design programme has been extended to analyse and incorporate any impacts associated with recent and proposed changes to Hāwea’s urban growth boundary, with associated funding of $0.8M proposed for deferral to 24/25. The project team is revising the construction programme to understand any potential impacts to the originally forecast practical completion date, and liaising closely with the Infrastructure Acceleration Fund management team within Kainga Ora regarding likely changes to funding milestones. | Wanaka-Upper Clutha
[7 empty] | Project Shotover Plant Upgrade: YTD Budget $2.3M with Actuals of $2.2M (Full year budget $14.1M) Construction contract awarded to McConnell Dowell. Physical works commenced August 2023 and due to be completed December 2025. | Queenstown-Whakatipu
[7 empty] | Kingston HIF new scheme Wastewater: YTD Budget $130k with Actuals of $36k (Full year budget $14.7M) Consultation with the Three Waters National Transition Unit and funding determinations are pending. | Queenstown-Whakatipu
[7 empty] | North Wānaka Conveyance Wastewater: YTD Budget $61k with Actuals of $82k (Full year budget $7.6M) The project is being delivered in two stages; (1) Aubrey Road conveyance, and (2) Beacon Point Rd Pump Station. Stage 1 completed June 2023. Stage 2 pump station appealed by submitters at hearing with mediation planned for November 23 and 24. $7.4M proposed to defer to 2024-2026 through the LTP24 draft process. | Wanaka-Upper Clutha
[7 empty] | CBD to Frankton Conveyance Wastewater: YTD Budget $1.3M with Actuals of $1M (Full year budget $5.6M) Sewer relining works underway April 2023 with forecast completion date by June 2024. Detailed design for the planned new rising main has commenced, with construction anticipated to commence in 24/25 subject to securing necessary planning permissions. | Queenstown-Whakatipu
PMO - Project Management Office | Water Supply | 4260957.86 | 5320934.75 | 1059976.89 | 20522764.08 | 20.76% | Shotover Country New Water Treatment Plant: YTD Budget $235k with Actuals of $263k (Full year budget $549k) Physical works complete. Awaiting final sign off for practical completion expected November 23. | Queenstown-Whakatipu
[7 empty] | Glenorchy Reservoir upgrade: YTD Budget $1.3M with Actuals of $1.2M (Full year budget $3M) Construction due to be completed October 23. Surplus budget to be transferred to Glenorchy Water Treatement Plant and Beacon New Reservoir projects. | Queenstown-Whakatipu
[7 empty] | Beacon Point new Reservoir: YTD Budget $3.3M with Actuals of $2.6M (Full year budget $4M) Construction commenced in December 2022 and main works forecast to be completed by December 2023. Additional funding is required to complete the project; this increase can be managed within other three waters cost centres and is proposed via the December 2023 Capital Reforecast. Negotiations with the contractor will determine the final value of the budget increase required. | Wanaka-Upper Clutha
[7 empty] | Luggate Water Supply Scheme: YTD Budget $145k with Actuals of $77k (Full year budget $24k) Detailed design completed March 23. Construction phase on hold pending Council re-prioritisation process associated with capital planning for draft LTP24. Budget increase of $0.2M proposed through the December reforecast to cover land acquisition and planning activities. | Wanaka-Upper Clutha
[7 empty] | Kingston HIF New Scheme Water Supply: YTD Budget $44k with Actuals of $31k (Full year budget $8.1M) Detailed design of the scheme is complete, with Stage 1 ready for construction procurement (Stage 1 includes construction of a new water treatment plant, reservoir, and rising and falling water supply main). Consultation with the Three Waters National Transition Unit and funding determinations are pending. Next step is to go to market for construction. | Queenstown-Whakatipu
[7 empty] | Quail Rise Reservoir: YTD Budget $181k with Actuals of $36k (Full year budget $839k) Detailed design approved by ECG July 23. No construction planned by QLDC until circa 2029-2030. Practical completion for Arrow Irrigation works October 23. Balance of 23/24 funds for planning / designation activities. | Queenstown-Whakatipu
[7 empty] | Glenorchy Water Treatment Plant: YTD Budget $81k with Actuals of $25k (Full year budget $53k) Detailed design updates due to be finalised October 23 and a consent application lodged. Construction has been deprioritised and deferred to 25/26 due to funding constraints. | Queenstown-Whakatipu
[7 empty] | Western Wānaka Level of Service Water Supply: YTD Budget $3k with Actuals of $7k (Full year budget $769k) Practical completion March 23 for main Heb contract capitalised 22/23. Agreed scope changes to include delivery of other parts of the ultimate conveyance route (to be funded from the project's forecast surplus) have been approved. Works for stage 2 (Alpha Series pipeline) has now been completed with stage 3 (further extensions to Alpha Series pipeline) to be completed 23/24. | Wanaka-Upper Clutha
[7 empty] | Cardrona Water Supply Scheme Pipeline: YTD Budget $42k with Actuals of $47k (Full year budget $3.1M) Construction contract awarded October 23, with forecast completion May 24. Surplus budget to be transferred to fund cost overrun forecast for Beacon point New Reservoir project. | Wanaka-Upper Clutha
PMO - Project Management Office | Transport | 48515.75 | 515082 | 466566.25 | 7436299.76 | 0.6524% | Whakatipu Active Travel Network: YTD Budget $6k with Actuals of $22k (Full year budget $186k) This budget is presently supporting design of route A8 (Lake Hayes Estate to Frankton). In addition, the funding provides for an assessment of potential bridge alignments across the Kawarau River to facilitate the A7 route (Jacks Point to Frankton) including the ability to cater for future 3W infrastructure. Peer review completed July identified higher cost. Internal meeting 21st Sept to guide next steps. Agreed 2 offers for service required for more investigation (of bridge from Frankton over Kawarau) and for consenting of the Lake Hayes Estate Bridge (with construction likely to be funded by the trails trust) over the Kawarau. | Queenstown-Whakatipu
[7 empty] | Arthurs Point to CBD Active Travel: YTD Budget $509k with Actuals of $26k (Full year budget $7.3M) Transport Choices Funded. Construction to commence September and forecast to complete by May 24. Potential underspend forecast, with permission pending with Waka Kotahi to spend balance on other parts of the route. | Arrowtown-Kawarau
PMO - Project Management Office | Buildings | 1653460.9 | 1859504 | 206043.1 | 2083325.82 | 79.37% | Paetara Aspiring Central: YTD Budget $1.9M with Actuals of $1.7M (Full year budget $2.1M) Practical completion reached September 23. Minor close out works to follow. Centre now open to the public. | Wanaka-Upper Clutha
PMO - Project Management Office | 3 Waters | 25706.3 | 0 | -25706.3 | 0 | 0% | Programme Management Costs reallocated to projects monthly. | District
Strategic Projects | Manawa - Project Connect & Civic Heart | 40952.69 | 13423.9 | -27528.79 | 73745.34 | 55.53% | Council office: Council continues to work with Ngāi Tahu Property (NTP) through the 2019 Partnering Agreement to develop a holistic plan for the Stanley Street site to deliver an integrated development of community facilities, commercial buildings, and a Council office. Councillors have approved community consultation on a first steps which are a proposed land exchange strategy to optimise land use and commercial terms, and a joint venture/Council Controlled Organisation with NTP to construct the Council office. | Queenstown-Whakatipu
Strategic Projects | 516 Ladies Mile Community Centre | 8993.07 | 11800 | 2806.93 | 3444998.75 | 0.261% | On hold pending Council re-prioritisation process associated with capital planning for draft 2024-34 Long Term Plan | Arrowtown-Kawarau
Strategic Projects | CIP - Crown Infrastructure Fund | 11820554.17 | 15245948.16 | 3425393.99 | 31685580.71 | 37.31% | Queenstown Arterial Stage 1: Three waters construction largely complete with minor works outstanding in Gorge Road and Melbourne Street (northern part). Other construction continues with a focus on underground services, structures and retaining walls. Construction sector cost escalation and availability of skilled resource remains a project risk being monitored. Any project or CAPEX adjustments will be brought to Council. Queenstown Street Upgrades: Construction complete on Park, Beach, Rees, Lower Brecon and Upper Brecon streets complete with full project practical completion due 22 December 2023. A modest surplus is forecast which will be confirmed once final Alliance and QLDC costs have been resolved. | Queenstown-Whakatipu
Strategic Projects | Lakeview Development - Subdivision Works | 2008125.95 | 2391768.79 | 383642.84 | 5335868.83 | 37.63% | Infrastructure works internal to the subdivision have been completed, with the remaining ancillary works along Thompson and Man Streets forecast to be substantively complete by late December 2023. The final project close out and handover is scheduled to be complete by March 2024. The forecast underspend in 23/24 is due to the $1.0M deferral to 24/25 proposed in the December Reforecast which is required to align payment with the developer-delivered swails due for completion in 24/25. | Queenstown-Whakatipu
Strategic Projects | Lakeview Development - Site Clearance | 11347.92 | 30000 | 18652.08 | 2628849.33 | 0.4317% | The Alliance has completed the known asbestos removal work. Remaining vacated cabins on site expected to be removed in 2024, after assessment of work and available budget. Some works may continue into 24/25 (timing of physical works to be confirmed once contract works confirmed). | Queenstown-Whakatipu
Strategic Projects | Lakeview Ancillary | 2734042.05 | 2908331.96 | 174289.91 | 6390781.34 | 42.78% | The Alliance current programme anticipates completion by the end of December 2023, with final handover of the site early in 2024. | Queenstown-Whakatipu
| TOTAL | 36198836.54 | 48315443.51 | 12116606.97 | 245371495.8 | 14.75%