## Sheet1
Finance YTD CAPEX Project Report - July 2023 to March 2024
`
[9 empty] | Per CPLAN (Infl to 22/23 $'s) | Per CPLAN (Infl to 22/23 $'s)
| Programme | 2023/24 Actuals Mar YTD | 2023/24 Budget Mar YTD | Variance YTD | 2023/24 Full Year Adjusted Budget | % of Full Year Budget Spent | Comments | Ward | 2022/23 Budget | 2023/243 Budget
Assurance, Finance & Risk | Not Applicable | 0 | 24464 | 24464 | 159486 | 0% | Procurement Systems (IN): YTD Budget $0k with Actuals of $0k (Full year budget $123k) - 23/24 for QLDC wide procurement strategy implementation. Awaiting recruitment of a Procurement Manager. Budget needed but wont be utilised until 2024/25. | District | #REF! | #REF!
Community Services | Libraries | 253533 | 310487 | 56954 | 439053 | 57.75% | Library Stock - District Wide: YTD Budget $265k with Actuals of $242k (Full year budget $371k) - Programmed to spend. | District | #REF! | #REF!
[7 empty] | Frankton Libraries Furniture and Equipment: YTD Budget $9k with Actuals of $0k (Full year budget $13k) - Frankton/Kingston minor renewals programmed | Queenstown-Whakatipu
[7 empty] | Whakatipu Libraries Furniture and Equipment: YTD Budget $18k with Actuals of $2k (Full year budget $27k) - Minor improvements programmed for Arrowtown/Glenorchy/Queenstown Libraries. | Queenstown-Whakatipu
[7 empty] | Upper Clutha Libraries Furniture and Equipment: YTD Budget $18k with Actuals of $10k (Full year budget $27k) - Minor improvements for Hawea/Wanaka Libraries | Wanaka-Upper Clutha
Community Services | Parks and Reserves | 1806833 | 2875266 | 1068433 | 4023035 | 44.91% | Tracks and Trails Renewals: YTD Budget $324k with Actuals of $201k (Full Year Budget $549k) - Whakatipu focus is Gibbston Trail upgrade, Thompson Street to Fernhill connection (active travel route B2) and Arrowtown Chinese Village trail realignment. Wanaka focus is Millenium trail, Wanaka Lakefront to Glendhu Bay and Upper Clutha River trail resurfacing. Districtwide contract tenders under review April with delivery May/June. | District | #REF! | #REF!
[7 empty] | Tree Planting Programme: YTD Budget $145k with Actuals of $124k (Full Year Budget $216k) - Spring planting programme completed. Autumn planting programme underway with planting scheduled April/May 2024. | District
[7 empty] | Playground Renewals: YTD Budget $376k with Actuals of $109k (Full year budget $405k) - Whakatipu focus is Mcbride Park playground feature replacements and flying foxes (Mcbride, Jardine, Hanleys) to be complete by June. Wanaka budget increased in the December 2023 Reforecast to enable the Luggate Playground installation (completed May 2024). | District
[7 empty] | Parks Roading Renewals: YTD Budget $420k with Actuals of $270k (Full year budget $644k) - Works undertaken November 2023 - March 2024 (awaiting final costs). | District
[7 empty] | Light Pole Replacements & Amenity Lighting: YTD Budget $150k with Actuals of $49k (Full Year Budget $263k) - order confirmed April ($115k) for upgrade of Queenstown Gardens and St Omer Park Lighting. Balance to be carried forward to FY2024/25 for delivery due to timing of international delivery. | District
[7 empty] | Toilet Renewals: YTD Budget $616k with Actuals of $361k (Full Year Budget $904k) - Northlake toilet completed March 2024. Contract agreed for implementation of toilets at Marine Parade, Shotover Country Sportsfield (planned for delivery May/June). | District
Community Services | Venues and Facilities | 414606 | 716574 | 301968 | 864316 | 47.97% | Queenstown Events Centre Alpine Aqualand Plant andEquipment Renewals: YTD Budget $398k with Actuals of $120k (Full year budget $424k) - $150k ringfenced for Wanaka Basketball hoops and $100k to Wanaka Lakefront Development Plan as per approved transfers in the May Reforecast. Balance of works during June 2024 shutdown (hydroslide works). | Queenstown-Whakatipu | #REF! | #REF!
[7 empty] | Queenstown Events Centre - Fit Out Renewals: YTD Budget $133k with Actuals of $129k (Full year budget $186k) - - Utilised for cricket wickets, fencing and minor equipment. | Queenstown-Whakatipu
[7 empty] | Wanaka Pool - Plant and Equipment Renewals: YTD Budget $79k with Actuals of $65k (Full year budget $108k) - Works to be completed during June shutdown. | Wanaka-Upper Clutha
Community Services | Buildings | 35681 | 25000 | -10681 | 25000 | 0% | Ballantyne Road Recreation Centre - WW Site preparation: YTD Budget $25k with Actuals of $21k (Full year budget $25k) - On hold pending Council re-prioritisation process associated with capital planning for draft Long Term Plan 2024-2034. | Wanaka-Upper Clutha | #REF! | #REF!
Community Services | Parks and Reserves | 1535665 | 4948795 | 3413130 | 7384411 | 20.8% | Wanaka Lakefront Development Plan Stage 2: YTD Budget $308k with Actuals of $255k (Full year budget $325k) - Stage 2 - Construction completed May 2023 with minor works including tiles, now completed August 2023. Issue raised in terms of tiles meeting requirements, QLDC is investigating this with the designer and contractor. Further update will be required at the appropriate time. | Wanaka-Upper Clutha | #REF! | #REF!
[7 empty] | Wanaka Lakefront Development Plan Stage 5: YTD Budget $600k with Actuals of $18k (Full year budget $1.5M) - Detailed design completed March 2024. Construction procurement underway April with physical works likely to commence by July, following approval of budget transfers in the May reforecast Council paper. | Wanaka-Upper Clutha
[7 empty] | Coronet Forest Revegetation: YTD Budget $1.7M with Actuals of $154k (Full year budget $2.6M) - Planting manager contract awarded. Planting contractor awarded March 2024. $1.9M balance likely to require carry-forward at year end. | Arrowtown-Kawarau
[7 empty] | Water Sports Facility and Parking - Wanaka: YTD Budget $420k with Actuals of $139k (Full year budget $624k) - Contract awarded February 2024. Works commenced March 2024 and on track for completion May 2024 for new footbridge and track. Carpark improvements under roading contract. | Wanaka-Upper Clutha
[7 empty] | Glenorchy Carpark & Marina Improvements: YTD Budget $500k with Actuals of $58k (Full year budget $723k) - Detailed design completed March 2024. Construction procurement to commence May with physical works likely to commence by July, following approval of budget increase in the May reforecast Council paper. | Queenstown-Whakatipu
Community Services | Venues and Facilities | 159002 | 248483 | 89481 | 323483 | 49.15% | Frankton Golf Course Reconfiguration: YTD Budget $225k with Actuals of $135k (Full year budget $300k) - Completion of golf course works January-April 2024 to be offset with Waka Kotahi funding. Club house works planned May 2024. | Queenstown-Whakatipu | #REF! | #REF!
[7 empty] | Queenstown Events Centre - Carpark Reconfiguration: YTD Budget $23k with Actuals of $23k (Full year budget $23k) - Masterplan concept design completed 2022/23. On hold pending council re-prioritisation process associated with capital planning for draft Long Term Ppla 2024-2034. | Queenstown-Whakatipu
Corporate Services | Information Management | 641502 | 1108480 | 466978 | 1497520 | 42.84% | Enterprise System: YTD Budget $443k with Actuals of $417k (Full year budget $603k) - Work scheduled to be delivered including the TechOne project pipeline; Resource backfill to support TechnologyOne CiA transition programme and Sentient.. | District | #REF! | #REF!
[7 empty] | ICT Projects: YTD Budget $208k with Actuals of $41k (Full year budget $286k) - Work scheduled to be delivered including Laptop cybersecurity upgrade, Cloud maturity support, backup audit, Digital Strategy Support, Information Management Transformation project support. | District
[7 empty] | ICT Network: YTD Budget $172k with Actuals of $29k (Full year budget $236k) - Work scheduled to be delivered including network improvement projects, IoT Platform enhancements, Wi-Fi and switch upgrades | District
Corporate Services | Libraries | 70946 | 196138 | 125192 | 269690 | 26.31% | Library Systems: YTD Budget $196k with Actuals of $71k (Full year budget $270k) - Improvements incl Libraries Website, Security gates Arrowtown and Hawea March/April, Humanforce project January/February start, RFID wands. | District | #REF! | #REF!
Corporate Services | Not Applicable | 14635 | 13979 | -656 | 20969 | 69.79% | Emergency Management: YTD Budget $14k with Actuals of $15k (Full year budget $21k) - Data projector emergency operations equipment purchased. | District | #REF! | #REF!
Infrastructure | Buildings | 434476 | 1150806 | 716330 | 1502399 | 28.92% | Gorge Road Office Civic Building - Renewal: YTD Budget $169k with Actuals of $172k (Full year budget $244k) - Toilet reconfiguration complete January 2024. Furniture/desks replacements, lighting and security ongoing. | Queenstown-Whakatipu | #REF! | #REF!
[7 empty] | Waterways Jetty/Ramp/Pontoon renewals - Districtwide: YTD Budget $593k with Actuals of $86k (Full year budget $774k) - Minor remedial works likely to commence by June 2024 across 3 prioritised sites (Kingston, Sunshine Bay and Bobs Cove Jetties). Balance reprioritised to be spent on detailed design to guide Long Term Pplan 2024-2034 improvement programme. Unlikely will be able to spend budget prior to year end June (risk that may not be able to carry forward renewals budget to 2024/25). | District
[7 empty] | Healthy Homes: YTD Budget $229k with Actuals of $103k (Full year budget $271k) - Phase 2: Arrowtown/Wanaka completed August-November 23. Balance of works to spend by June incl Ballarat Street Flats and 2A/B Shotover Street. | District
Infrastructure | Camp Grounds | 3568 | 59500 | 55932 | 66381 | 5.375% | Campgrounds - Minor Capex: YTD Budget $60 with Actuals of $4k (Full Year Budget $66k) - Budget reallocated in the May reforecast. | District | #REF! | #REF!
Infrastructure | Libraries | 104604 | 69856 | -34748 | 86010 | 121.6% | Libraries Building Renewals: YTD Budget $66k with Actuals of $99k (Full Year Budget $81k) - Emergency works completed to remove borer and reinstate wall linings and floors at Kingston Library. Minor adj included in the May reforecast to increase budget. | District | #REF! | #REF!
Infrastructure | Transport | 4986104 | 6166682 | 1180578 | 8662865 | 57.56% | Sealed road resurfacing: YTD Budget $2.1M with Actuals of $1.9M (Full Year Budget $2.2M) - Majority of Downer contract programme completed. | District | #REF! | #REF!
[7 empty] | Sealed road pavement rehabilitation: YTD Budget $1.4M with Actuals of $1.3M (Full Year Budget $2.5M) - Contract awarded for Cardrona Valley Road and Lower Shotover Road rehab works with works programmed for December 2024 - April 2025 Sealing season. | District
[7 empty] | Unsealed road metalling: YTD Budget $939k with Actuals of $308k (Full year budget $1.4M) - Budgets aligned with Waka Kotahi funding. Rolling Downer contract to complete works. | District
[7 empty] | Queenstown Comprehensive Parking Management Plan: YTD Budget $239k with Actuals of $338k (Full year budget $394k) - Parking management strategy contract has been awarded to Stantec and to be completed by June year end. | District
Infrastructure | Venues and Facilities | 111713 | 95499 | -16214 | 120852 | 92.44% | Wanaka Arts Centre - Building Renewals: YTD Budget $39k with Actuals of $4k (Full year budget $50k) - Contract awarded for internal/external painting. | Wanaka-Upper Clutha | #REF! | #REF!
[7 empty] | Arrowtown Hall - Renewals: YTD Budget $0k with Actuals of $0k (Full year budget $24k) - Budget reallocated in the May Reforecast. | Arrowtown-Kawarau
[7 empty] | Queenstown Events Centre - Building Renewals: YTD Budget $12k with Actuals of $83k (Full year budget $14k) - Budget increased to $70k in the May Reforecast for emergency HVAC upgrades, lights, blinds and family change room. | Queenstown-Whakatipu
Infrastructure | Waste Management | 195145 | 851126 | 655981 | 1432461 | 13.62% | Existing Waste Site Consenting: YTD Budget $311k with Actuals of $43k (Full year budget $627k) - Landfill consent expires 2032. Morrison Low engaged to draft RFP, which is underway April followed by procurement for consenting. Remediation pricing for Tucker Beach consenting received & we have engaged Tonkin & Taylor to assist due to complexities with the process. Remediation repairs also required for consent at Wanaka closed landfill and Tuckers Beach. | District | #REF! | #REF!
[7 empty] | Existing Wakatipu Waste Facilities: YTD Budget $374k with Actuals of $136k (Full year budget $513k) - Proposal received from Waste Management on upgrades required. Heating completed. Commitments incl MRF Pit floor, rollers, belts & pipes. MRF prelim assessment/design for Frankton Transfer station underway. | Queenstown-Whakatipu
[7 empty] | Public Place Waste Bins: YTD Budget $90k with Actuals of $6k (Full year budget $159k) - 2023/24 focus on install of bins purchased 2022/23. Contractor expected to implement April-June. | District
Infrastructure | Storm Water | 253408 | 903848 | 650440 | 1234144 | 20.53% | 3 Waters Renewals: YTD Budget $3.5M with Actuals of $3.4M (Full Year Budget $4.4M) - Renewals Works programmed to spend full 2023/24 budget with overspend of $0.5M likely due to the Shotover Aeration Grid renewal which was urgently required, along with a high number of unscheduled urgent works. Rockabilly Gully Erosion Protection: (Stormwater) YTD Budget $239k with Actuals of $54k (Full year budget $308k) - Pricing received for design April 2024 is under review. May require further procurement to confirm expected costs. | District | #REF! | #REF!
| Waste Water | 674347 | 1818398 | 1144051 | 2720318 | 24.79% |  |  | #REF! | #REF!
| Water Supply | 2731471 | 1320345 | -1411126 | 1095178 | 249.4% |  |  | #REF! | #REF!
Infrastructure | Not Applicable | 12259 | 0 | -12259 | 0 | 0% | 3 Waters Reform Stimulus: close out - Costs to be reallocated to other renewals | District | #REF! | #REF!
Infrastructure | Buildings | 499309 | 796686 | 297377 | 1163832 | 42.9% | Luggate Hall Replacement: YTD Budget $258k with Actuals of $79k (Full year budget $361k) - Practical completion November 2022. Opened in December. Final claim received April 2024. Withholding $60k for Storm water defects/issues. Minor close out works to follow. | Wanaka-Upper Clutha | #REF! | #REF!
[7 empty] | Stanley St playcentre relocation: YTD Budget $233k with Actuals of $350k (Full year budget $350k) - One off payment of $350,000 to MoE towards the new facility. | Queenstown-Whakatipu
[7 empty] | Frankton Library Fitout of leased space: YTD Budget $183k with Actuals of $15k (Full year budget $203k) - Design modified for new leased area. Procurement underway April 2024. | Queenstown-Whakatipu
Infrastructure | Waste Management | 393283 | 1040279 | 646996 | 4150316 | 9.476% | Whakatipu New Waste Facilities: YTD Budget $16k with Actuals of $77k (Full year budget $2.8M) - Budget used for land purchase in Wanaka January 2024 with transfer of budget approved in the May Reforecast. Procurement for site strategic analysis work underway March 2024 (incl location of MRF) to guide options. | Queenstown-Whakatipu | #REF! | #REF!
[7 empty] | Organic Waste Management: YTD Budget $421k with Actuals of $121k (Full year budget $467k) - Forecast to spend $651k which is an additional $184k that will be reimbursed by MFE (milestone dates Feb/Mar 24) to support kerbside collections, Grow Wanaka and Zero Waste Glenorchy initiatives. | District
[7 empty] | Zero Waste District Programme: YTD Budget $451k with Actuals of $184k (Full Year Budget $695k) - Service agreements in place which will incur milestone payments (Resourceful communities $212k, Wanaka Community Workshop $41k, One Bike Lightfoot Initiative $39k, Kiwi Harvest $38k, Zero Waste Event work $30k, WAO Circular Economy Programme $108k). | District
Infrastructure | Storm Water | 443982 | 869237 | 425255 | 1246341 | 35.62% | Catchment Management Plans - Whakatipu and Wanaka YTD Budget $283k with Actuals of $132k (Full Year Budget $389k) - Contract committed to spend full amount across Whakatipuk/Wanaka. | District | #REF! | #REF!
[7 empty] | Investigations - Whakatipu and Wanaka: YTD Budget $255k with Actuals of $83k (Full Year Budget $382k) - Contract with E3 Scientific commenced March 2023 for $160k across Whakatipu/Wanaka across 21 locations over 2 years. A contract for stormwater level monitoring for $160k also commenced in May to run through 2023/24. | District
[7 empty] | Modelling - Whakatipu and Wanaka: YTD Budget $147k with Actuals of $128k (Full Year Budget $201k) - Commitments raised for modelling to feed into Catchment Management Plans. | District
Infrastructure | Waste Water | 391320 | 2067478 | 1676158 | 2497180 | 15.67% | Project Pure Aeration Grid Renewal: YTD Budget $1.3M with Actuals of $42k (Full year budget $1.3M) - Contract award has been delayed due to a requirement to incorporate additional scope into the project. Spend this FY will likely be limited to deposit payment on aeration equipment supply and some management/design costs (circa $500k). | Wanaka-Upper Clutha | #REF! | #REF!
[7 empty] | Masterplanning Waste Water: YTD Budget $221k with Actuals of $69k (Full year budget $308k) - Eastern corridor and Arrowtown Waste Water Optimisation study works ongoing along with internal work on strategic business cases for Upper Clutha. | Wanaka-Upper Clutha
Infrastructure | Water Supply | 15590064 | 17544211 | 1954147 | 18740920 | 83.19% | Cardrona Water Supply Scheme: YTD Budget $15.1M with Actuals of $14.8M (Full year budget $15.1M) - QLDC has made payment to the developer in March 2024 to acquire the new scheme. | Wanaka-Upper Clutha | #REF! | #REF!
[7 empty] | Demand Management - Hawea Water Supply: YTD Budget $816k with Actuals of $109k (Full year budget $1.5M) - A preferred contractor has been selected, and meter installation is programmed for commencement within the current financial year. Final contract negotiations ongoing to confirm the start date. | Wanaka-Upper Clutha
[7 empty] | Luggate Reservoir Capacity Water Supply: YTD Budget $260k with Actuals of $74k (Full year budget $290k) - Land purchase due for settlement May 2024 (circa $190k) following consenting/designation. Project to be placed on hold pending future funding for construction. | Wanaka-Upper Clutha
[7 empty] | Hydro Model and System Performance - Districtwide Water Supply: YTD Budget $346k with Actuals of $73k (Full year budget $479k) - Modelling underway on Queenstown bores and specific developments (Silver Creek / Coneburn) and Ladies Mile. | District
Infrastructure | Transport | 12281424 | 13839574 | 1558150 | 20069795 | 61.19% | Road to Zero Minor Improvements Programme Low Cost Low Risk: YTD Budget $7.0M with Actuals of $7.2M (Full year budget $10.1M) - Construction underway/scheduled for Hawthorne Road, Glenorchy Corridor, Lower Shotover Rd, Arrowtown RTZ, Riverbank/Ballantyne, Golf Road, Capell Ave, Wanaka Corridor, Anderson/Aubrey, Rata Street, Aubrey Road and Cardrona Village. Waka Kotahi Sub 51% subsidised budget. | District | #REF! | #REF!
[7 empty] | Wanaka Pool to School Active Travel: YTD Budget $3.4M with Actuals of $2.4M (Full year budget $5.0M) - Stage 2 Kellys Flat to Little Street nearing completion ($2.7M) of which $1.5M is Transport Choice Subsidy funded. Stage 3 State Highway to Ballantyne Road $1.4M contract awarded with works to run April-June. | Wanaka-Upper Clutha
[7 empty] | Whakatipu Active Travel Low Cost Low Risk: YTD Budget $998k with Actuals of $670k (Full year budget $1.4M) - Route B2 Thompson Street works due for completion April 2024 ($1.4M). Waka Kotahi Subsidy 51% budget. | Queenstown-Whakatipu
[7 empty] | Wanaka Active Travel Low Cost Low Risk: YTD Budget $439k with Actuals of $751k (Full year budget $601k) - Anderson Road Active travel completed February 2024. Minor close out works to follow. Waka Kotahi Subsidy 51% budget. | Queenstown-Whakatipu
[7 empty] | Whakatipu Public Transport Low Cost Low Risk: YTD Budget $322k with Actuals of $183k (Full year budget $662k) - Tranche 2 construction minor close out works to be completed by year end. Procurement of Tranche 3 design and associated bus shelters underway, following confirmation of priorities with ORC. ORC Subsidy 51% budget. | Queenstown-Whakatipu
[7 empty] | Wanaka Masterplan Update: YTD Budget $412k with Actuals of $359k (Full year budget $618k) - Contract for network optimisation single stage business case commenced September 2023 and due to be completed December 2024. Waka Kotahi Subsidy 51% budget. | Wanaka-Upper Clutha
Infrastructure | Venues and Facilities | 131244 | 250000 | 118756 | 368254 | 35.64% | Building Management System: YTD Budget $250k with Actuals of $127k (Full year budget $367k) - Designs complete. Implementation commenced March 2024 and to be completed by June. | District | #REF! | #REF!
Infrastructure | Not Applicable | 292386 | 346479 | 54093 | 381395 | 76.66% | Queenstown Priority Growth Corridors: YTD Budget $197k with Actuals of $195k (Full year budget $228k) - Establishment Report complete. Recruitment for a programme manager imminent. | Queenstown-Whakatipu | #REF! | #REF!
[7 empty] | Wanaka Airport Masterplan: YTD Budget $150k with Actuals of $97k (Full year budget $153k) - Draft Capital Plan and Functional Strategy delivered and integrated into draft Long Term Plan 2024-2034 preparations. Part 139 compliance deliverables have triggered the need to review Wanaka Airport management structure and the current services agreement in place. Investigative work underway to explore alternatives. | Wanaka-Upper Clutha
PMO - Project Management Office | Waste Management | 3448795 | 250979 | -3197816 | 1245129 | 277% | Wanaka New Waste Facilities: YTD Budget $251k with Actuals of $3.4M (Full year budget $1.2M) - Design contract awarded November 2023, concept design is due to complete June 24. $3.4M paid for Wanaka land purchase end of Jan (budget to be reallocated from Whakatipu New Waste facilities as approved in the May Reforecast). The current approved Long Term Plan budget is insufficient for the preferred upgrade solution. Work is underway to assess the cost and scope in more detail before the amount of new funding can be confirmed. | Wanaka-Upper Clutha | #REF! | #REF!
PMO - Project Management Office | Storm Water | 615560 | 114000 | -501560 | 557281 | 110.5% | Aubrey Road Recreation Reserve Stormwater detention pond: YTD Budget $4k with Actuals of $438k (Full year budget $430k) - Detailed design and construction of Aubrey Road pipeline complete. Minor remedial works undertaken 2023/24. Balance of project to be placed on hold until future funding is available for construction of the Kellys Flat detention pond. | Wanaka-Upper Clutha | #REF! | #REF!
[7 empty] | Kingston HIF New Scheme Stormwater: YTD Budget $110k with Actuals of $177k (Full year budget $127k) - Detailed design is complete and the earthworks consent has been granted. Procurement for construction underway April 2024. Anticipating construction to commence September 2024. | Queenstown-Whakatipu
PMO - Project Management Office | Waste Water | 20108308 | 18056448 | -2051860 | 23514538 | 85.51% | Marine Parade Pump Station Electrical Upgrade: YTD Budget $63k with Actuals of $78k (Full year budget $65k) - Detailed design is complete and notice of requirement (NOR) has been lodged to designate the new location for the pump station. The project will be placed on hold until future funding is available to construct the pump station. | Queenstown-Whakatipu | #REF! | #REF!
[7 empty] | Project Pure Upgrade Waste Water: YTD Budget $3.8M with Actuals of $4.3M (Full year budget $4.2M) - Construction completed December 2023 with final commissioning March 2024. $0.6M budget in 2024/25 will be required to be brought forward as a year end adjustment. | Wanaka-Upper Clutha
[7 empty] | Upper Clutha Conveyance Scheme: YTD Budget $864k with Actuals of $669k (Full year budget $1.0M) - Detailed design has commenced and is planned to be completed by early 2025. The design programme has been extended to analyse and incorporate potential design changes required to align with the latest Draft QLDC population forecasts. As a result, the project team is working with Kainga Ora to amend the funding milestones within the Delivery Plan included in the Infrastructure Acceleration Fund funding agreement. | Wanaka-Upper Clutha
[7 empty] | Project Shotover Plant Upgrade: YTD Budget $9.5M with Actuals of $12.2M (Full year budget $14.0M) - Physical works commenced August 2023 and due to be completed December 2025. Current 2023/24 forecast anticipates $4.4M budget in 2024/25 will be required to be brought forward as a year end adjustment. | Queenstown-Whakatipu
[7 empty] | Kingston HIF new scheme Waste Water: YTD Budget $122k with Actuals of $259k (Full year budget $146k) - Detailed design is underway and is expected to be completed late 2024 / early 2025. Current20 23/24 forecast anticipates $0.4M budget in 2024/25 will be required to be brought forward as a year end adjustment. | Queenstown-Whakatipu
[7 empty] | North Wanaka Conveyance Waste Water: YTD Budget $162k with Actuals of $222k (Full year budget $250k) - The project is being delivered in two stages; (1) Aubrey Road conveyance, and (2) Beacon Point Road Pump Station. Stage 1 completed June 2023. Stage 2 pump station still in consenting stage. Designation appealed by submitters and QLDC are considering the next phases (budget in years 1-3 of draft Long Term Plan 2024-2034). | Wanaka-Upper Clutha
[7 empty] | CBD to Frankton Conveyance Waste Water: YTD Budget $3.2M with Actuals of $2.0M (Full year budget $3.2M) - Sewer relining works underway April 2023 with forecast completion date by May 2024. Detailed design for the planned new rising main has commenced, with construction anticipated to commence early 2025. | Queenstown-Whakatipu
[7 empty] | Robins Road Conveyance Upgrade Waste Water: YTD Budget $294k with Actuals of $246k (Full year budget $580k) - Detailed design is underway, with construction forecast to commence in early 2025. | Queenstown-Whakatipu
PMO - Project Management Office | Water Supply | 13972294 | 15619254 | 1646960 | 20463439 | 68.28% | Shotover Country New Water Treatment Plant: YTD Budget $235k with Actuals of $359k (Full year budget $549k) - Physical works complete. Practical completion issued January 2024. | Queenstown-Whakatipu | #REF! | #REF!
[7 empty] | Glenorchy Reservoir upgrade: YTD Budget $2.4M with Actuals of $2.3M (Full year budget $2.4M) - The new reservoirs were commissioned in December 2023. | Queenstown-Whakatipu
[7 empty] | Beacon Point new Reservoir: YTD Budget $5.4M with Actuals of $4.8M (Full year budget $5.6M) - Main Reservoir tank works completed December 2023. Budget of $1.5M added in the December reforecast to complete construction of earth bund to screen future water treatment plant. Bund earthworks have been completed with planting/landscaping underway. | Wanaka-Upper Clutha
[7 empty] | Luggate Water Supply Scheme: YTD Budget $158k with Actuals of $220k (Full year budget $230k) - Detailed design completed March 2023. Land purchase completed February 2024. Construction phase on hold due to reprioritisation of budgets. Now programmed to commence 2027. | Wanaka-Upper Clutha
[7 empty] | Kingston HIF New Scheme Water Supply: YTD Budget $89k with Actuals of $92k (Full year budget $104k) - Detailed design is complete. Currently out to market with Stage 1 construction procurement (Stage 1 includes construction of a new water treatment plant, reservoir, and rising and falling water supply main). Contract award anticipated July 2024. Current 2023/24 forecast anticipates $0.1M budget in 2024/25 will be required to be brought forward as a year end adjustment. | Queenstown-Whakatipu
[7 empty] | Quail Rise Reservoir: YTD Budget $176k with Actuals of $165k (Full year budget $190k) - Detailed design complete and planning/designation activities ongoing. Project will be placed on hold until future funding is available for construction. | Queenstown-Whakatipu
[7 empty] | Glenorchy Water Treatment Plant: YTD Budget $113k with Actuals of $88k (Full year budget $113k) - Detailed design scheduled for completion by June year end with consent applications lodged shortly after. Project will be placed on hold until future funding is available for construction. | Queenstown-Whakatipu
[7 empty] | Western Wanaka Level of Service Water Supply: YTD Budget $94k with Actuals of $21k (Full year budget $408k) - Practical completion March 2023 for main Heb contract. Final defects close out in process, with final remediations underway. Agreed scope changes to include delivery of other parts of the ultimate conveyance route (to be funded from the project's forecast surplus) have been approved. Works for stage 2 (Alpha Series pipeline) has now been completed with stage 3 (further extensions to Alpha Series pipeline) planned to commence May 2024. | Wanaka-Upper Clutha
[7 empty] | Cardrona Water Supply Scheme Pipeline: YTD Budget $1.3M with Actuals of $1.2M (Full year budget $2.4M) - Construction contract commenced November 2023, with forecast completion May 2024. | Wanaka-Upper Clutha
[7 empty] | Compliance Response - UV Treatment Water Supply: YTD Budget $5.6M with Actuals of $4.7M (Full year budget $8.5M) - Fernhill, Western Intake and Beacon Point UV treatment now completed. Smaller UV locations to be rolled out for remainder of year (Corbridge, Wanaka Airport, Luggate, Glenorchy). Two Mile intake subject to planning requirements. All locations must be completed by 31 December 2024. | District
PMO - Project Management Office | Transport | 3986594 | 5092082 | 1105488 | 7436300 | 53.61% | Whakatipu Active Travel Network: YTD Budget $83k with Actuals of $31k (Full year budget $186k) - No further expenditure planned for 2023/24; Budget reallocated to Wanaka Lakefront Development Plan Stage 5 in the May reforecast. | Queenstown-Whakatipu | #REF! | #REF!
[7 empty] | Arthurs Point to CBD Active Travel: YTD Budget $5M with Actuals of $4M (Full year budget $7.3M) - Construction commenced September 2023 and is forecast to complete by May 2024. QLDC currently assessing opportunity to utilise surplus budget to deliver additional scope. | Arrowtown-Kawarau
PMO - Project Management Office | Buildings | 2029440 | 2566480 | 537040 | 2607322 | 77.84% | Paetara Aspiring Central: YTD Budget $2.1M with Actuals of $2.0M (Full year budget $2.1M) - Construction commenced April 2023 and practical completion reached September 2023. Additional budget transfers approved of $200k in the May reforecast for Basketball hoops. | Wanaka-Upper Clutha | #REF! | #REF!
[7 empty] | Performing Arts Centre: YTD Budget $483k with Actuals of $27k (Full year budget $524k) - Works commenced April to demolish the Playcentre and for removal of QPAC to relocate to Country Lane. Programmed to be completed by June 2024. | Queenstown-Whakatipu
PMO - Project Management Office | 3 Waters | -4046 | 0 | 4046 | 0 | 0% | Programme Management Costs reallocated to projects monthly. | District | #VALUE! | #VALUE!
Strategic Projects | Manawa - Project Connect & Civic Heart | 72698 | 50297 | -22401 | 73745 | 98.58% | Project Connect Civic Administration Building: On 31 August 2023 Councillors adopted a Statement of Proposal (SOP) for community consultation before the end of 2023 on a land strategy for the Site and joint venture arrangements between the parties. On 4 April 2024, following community consultation and a hearing, councillors adopted the land strategy for the Site and decided not to progress the joint venture arrangement with NTP. There are a number of steps to achieve the proposed land strategy involving QLDC’s existing partnership with NTP and their various rights and interests in the site, including a right of first refusal, and Ministerial approval. Staff have been directed to report back to the Council with a scope of works programme for the land strategy. | Queenstown-Whakatipu | #REF! | #REF!
Strategic Projects | Queenstown Strategic Land Purchases | 0 | 0 | 0 | 0 | 0% | For reallocation of 2A/B Shotover St Land and Ballarat St Apartment purchases that were allocated to Arterials but were purchased for strategic purposes and are assets likely to be onsold. Budget to be added as approved in the May reforecast. | District | #REF! | #REF!
Strategic Projects | CIP - Crown Infrastructure Fund | 35800416 | 37971403 | 2170987 | 48333585 | 74.07% | Queenstown Town Centre Arterials - CIP Stage 1: YTD Budget $33.5M with Actuals of $30.9M (Full year budget $44.2M) - As at 31 March 2024 side road construction works on Frankton Road have been completed, pavement works in Melbourne Street have recommenced and stormwater installations in Zone 3 are ongoing. Retaining wall works at St Joseph’s church are still ongoing - piling works have been completed and backfilling is well progressed. There has been a delay in the completion of the St Joseph’s retaining wall due to complexities in the shop drawings, causing a delay in manufacturing the balustrades. The estimated completion date for this work is 30 June 2024. Queenstown Street Upgrades - CIP: YTD Budget $4.5M with Actuals of $4.9M (Full year budget $4.1M) - As at 31 March 2024 construction is complete with minor works (minor faults and omissions) underway in parallel to submission of the final Quality Assurance Documents. The budget and forecast for 2023/24 allows for an anticipated credit of circa $4.0M to be received in June 2024 for the Alliances pain/gain share. | Queenstown-Whakatipu | #REF! | #REF!
Strategic Projects | Lakeview Development - Subdivision Works | 4796147 | 3611512 | -1184635 | 4335869 | 110.6% | Infrastructure works internal to the subdivision have been completed. The final project close out and handover is scheduled to be complete by April 2024 but is reliant on completion of Ancillary project work. Note a $1.0M deferral to 24/25 was approved in the December Reforecast which was required to align payment with the developer-delivered swails due for completion in 24/25. Investigating internally the allocation of Alliance final close out costs which is increasing the forecast when the project should be in final close out stage. | Queenstown-Whakatipu | #REF! | #REF!
Strategic Projects | Lakeview Development - Site Clearance | 868087 | 1206202 | 338115 | 2846059 | 30.5% | The Alliance has completed the known asbestos removal work. Remaining vacated cabins on site expected to be removed in 2024, tender assessment has been completed and contractor has commenced works in March and due for completion June 2024. | Queenstown-Whakatipu | #REF! | #REF!
Strategic Projects | Lakeview Ancillary | 6347126 | 5911873 | -435253 | 6390781 | 99.32% | The Alliance current programme is predominantly complete on Man/Thompson Streets, with final handover in April. Awaiting confirmation of revised dates to complete existing Isle St surface upgrades. | Queenstown-Whakatipu | #REF! | #REF!
| TOTAL | 136503929 | 150108200 | 13604271 | 198349632 | 68.82% |  |  | #REF! | #REF!
|  | #REF! | #REF! | 0 | #REF! |  |  |  | #REF! | #REF!